## ProductBacklog
No | Features | Related Features | Role | User Story | Estimate | Status
1 | Login |  | Guest
2 | Logout |  | Admin, User
| User Profile |  | User
3 | Register new account
4 | Mapping current account and friend list from social network (facebook, google+) | 1
5 | Update profile info: Interest, gender, location,… | 6
6 | View profile | 3,5
| Manage Friend List |  | User
7 | Search new friend | 6
8 | View friend list | 4
9 | Add new friend | 6
10 | Unfriend / block friend | 6
| Scan Nearby Friend |  | User
11 | Get current position
12 | View grib view nearby friend | 11
13 | View location map with friend position | 11
14 | View people nearby you by matching profile | 11,19
| Suggest Friend |  | User
15 | Suggest friend use might want to meet | 19
| Realtime chat |  | User
16 | Realtime chat, message with available friends | 8
17 | View chat history | 16
| Notification |  | User
18 | Receive notification when friends are nearby | 11
Recommender System
19 | Recommerder system to suggest friends base on user profile similarity
| User management |  | Admin
20 | View user of the system
21 | Change user status | 20

## SPRINT1
SPRINT 1 |  |  | Start | 2015-12-05
|  |  | End | 18/5/2015
No. | Task | Description | PIC | Status | Est. | Day
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Design mockup UI |  | ThangPV | Finished | 4 | 0
2 | Design main layout |  | ThangPV | Finished | 16 |  | 11 | 6 | 1 | 0
3 | Design UseCase |  | ThangPV | Finished | 4 | [5 empty] | 0
4 | Design ERD |  | ThangPV | Finished | 4 | [5 empty] | 2 | 0
5 | Design chat UI |  | KhuongMH | Inprocess | 14 | 9 | 7 | 5 |  |  | 0
6 | Design scan nearby user UI |  | KhuongMH | Finished | 14 | [5 empty] | 11 | 0
7 | Design login/social network connection |  | HungLV | Inprocess | 14 |  | 12 | 10 | 8 |  | 4 | 0
8 | Design setting user profile |  | HungLV | Inprocess | 14 |  | 12 | 10 | 8 |  | 4 | 0
9 | Design friends list UI |  | KhoaVNA | Finished | 14 |  |  | 10 | 4 | 1 |  | 0
10 | Design Utilities layout |  | KhoaVNA | Finished | 14 |  |  |  |  | 12 | 8 | 0
11 | Report 1 |  | KhoaVNA | Finished | 4 | 2 | 1.5 | 0
SPRINT REPORT
SPRINT TASKS
| Total Task | 11
| Finished | 8
| Inprocess | 3
TEAM PERFORMANCE
| Member | Total Task | Finished | Percent
| ThangPV | 4 | 4 | 100%
| KhuongMH | 2 | 1 | 50%
| HungLV | 2 | 0 | 0%
| KhoaVNA | 3 | 3 | 100%

## SPRINT2
SPRINT 2 |  |  | Start | 19/5/2015
|  |  | End | 25/5/2015
No. | Task | Description | PIC | Status | Est | Day
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | <Client> Integrating google plus login function | Get user details and their friends | HungLV | Inprocess | 10 |  |  |  |  | 7 | 4 | 1
2 | <Client> Integrating facebook login function | Get user details and their friends | HungLV | Inprocess | 10 | 5 | 0
3 | Design register UI |  | HungLV | Inprocess | 4 |  |  | 4
4 | <Client> Register function |  | HungLV | Inprocess | 8 |  |  | 6 | 0
5 | <Client> Get current user position function | Android Location API using Google Play Services | KhuongMH | Finished | 14 | 6 | 4 | 3 | 0
6 | <Client> JSON parser function |  | KhuongMH | Finished | 4 | 0
7 | <Client> Send, receive chat/message function |  | KhuongMH | Inprocess | 14 |  | 13 | 9 | 6
8 | <Client> Notification function |  | KhoaVNA | Inprocess | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0
9 | <Client> Profile management function | Allow user update, their profile | KhoaVNA | Inprocess | 12 |  |  |  | 10
10 | Report 2 |  | KhoaVNA | Finished | 8 | 6 | 5 | 3 | 0 | 0 | 0 | 0
11 | <Server> Webservice for retreive user information | login, register , and profile info | ThangPV | Finished | 20 | 18 | 16 | 12 | 8 | 6 | 3 | 0
12 | Design Neo4j Database |  | ThangPV | Finished | 8 |  |  |  | 6 | 4 | 2 | 0
13 | Design Admin Dashboard |  | ThangPV | Finished | 4 | 2 | 1 | 0
14 | Design chat UI | Continue from SPRINT 1 | KhuongMH | Inprocess | 4
15 | Design login/social network connection | Continue from SPRINT 1, Transfer from HungLV | ThangPV | Finished | 4 |  | 0
16 | Design setting user profile | Continue from SPRINT 1 | HungLV | Inprocess | 4
SPRINT REPORT
SPRINT TASKS
| Total Task | 16
| Finished | 0
| Inprocess | 0
TEAM PERFORMANCE
| Member | Total Task | Finished | Percent
| ThangPV | 0 | 0 | #DIV/0!
| KhuongMH | 0 | 0 | #DIV/0!
| HungLV | 0 | 0 | #DIV/0!
| KhoaVNA | 0 | 0 | #DIV/0!

## SPRINT3
SPRINT 3 |  |  | Start | 19/5/2015
|  |  | End | 26/5/2015
No. | Task | Description | PIC | Status | Est | Day
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
1
2
3
4
5
6
7
8
9
10
SPRINT REPORT
SPRINT TASKS
| Total Task | 10
| Finished | 0
| Inprocess | 0
TEAM PERFORMANCE
| Member | Total Task | Finished | Percent
| ThangPV | 0 | 0 | #DIV/0!
| KhuongMH | 0 | 0 | #DIV/0!
| HungLV | 0 | 0 | #DIV/0!
| KhoaVNA | 0 | 0 | #DIV/0!

## Project Coreflow
4 main coreflow are listed below:
1 | Create user profile (connect automatically with their social network) | KhoaVNA
2 | Manage friends list
3 | Scan near-by locations to find people around the user | ThangPV
4 | Matching user’s interest and profile with others
5 | Suggest user’s people they might want to meet based on their friend’s connections | HungLV
6 | Real time chat & notification when events happen | KhuongMH

## Question
1 | Scan near-by location / Matching user's interest and profile with other là 2 function khác nhau hay là 1 ( trong khi scan thì chỉ suggest những user nào match)
2 | Create user profile. This feature should connect automatically to current user account on other social sites [Facebook, Google+, ..) là cho login qua facebook, google thôi hay là có thêm việc lấy list friends có sử dụng app này??
ilike

## Member
ThangPV
KhuongMH
HungLV
KhoaVNA

## TaskStatus
Not Start
Inprocess
Wait for Approve
Finished