## ProductBacklog
No | Features | Related Features | Role | User Story | Estimate | Status
1 | Login |  | Guest
2 | Logout |  | Admin, User
| User Profile |  | User
3 | Register new account
4 | Mapping current account and friend list from social network (facebook, google+) | 1
5 | Update profile info: Interest, gender, location,… | 6
6 | View profile | 3,5
| Manage Friend List |  | User
7 | Search new friend | 6
8 | View friend list | 4
9 | Add new friend | 6
10 | Unfriend / block friend | 6
| Scan Nearby Friend |  | User
11 | Get current position
12 | View grib view nearby friend | 11
13 | View location map with friend position | 11
14 | View people nearby you by matching profile | 11,19
| Suggest Friend |  | User
15 | Suggest friend use might want to meet | 19
| Realtime chat |  | User
16 | Realtime chat, message with available friends | 8
17 | View chat history | 16
| Notification |  | User
18 | Receive notification when friends are nearby | 11
Recommender System
19 | Recommerder system to suggest friends base on user profile similarity
| User management |  | Admin
20 | View user of the system
21 | Change user status | 20

## SPRINT1
SPRINT 1 |  |  | Start | 2015-12-05
|  |  | End | 18/5/2015
No. | Task | Description | PIC | Status | Est. | Day
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Design mockup UI |  | ThangPV | Finished | 4 | 0
2 | Design main layout |  | ThangPV | Finished | 16 |  | 11 | 6 | 1 | 0
3 | Design UseCase |  | ThangPV | Finished | 4 | [5 empty] | 0
4 | Design ERD |  | ThangPV | Finished | 4 | [5 empty] | 2 | 0
5 | Design chat UI |  | KhuongMH | Inprocess | 14 | 9 | 7 | 5 |  |  | 0
6 | Design scan nearby user UI |  | KhuongMH | Finished | 14 | [5 empty] | 11 | 0
7 | Design login/social network connection |  | HungLV | Inprocess | 14 |  | 12 | 10 | 8 |  | 4 | 0
8 | Design setting user profile |  | HungLV | Inprocess | 14 |  | 12 | 10 | 8 |  | 4 | 0
9 | Design friends list UI |  | KhoaVNA | Finished | 14 |  |  | 10 | 4 | 1 |  | 0
10 | Design Utilities layout |  | KhoaVNA | Finished | 14 |  |  |  |  | 12 | 8 | 0
11 | Report 1 |  | KhoaVNA | Finished | 4 | 2 | 1.5 | 0
SPRINT REPORT
SPRINT TASKS
| Total Task | 11
| Finished | 8
| Inprocess | 3
TEAM PERFORMANCE
| Member | Total Task | Finished | Percent
| ThangPV | 4 | 4 | 100%
| KhuongMH | 2 | 1 | 50%
| HungLV | 2 | 0 | 0%
| KhoaVNA | 3 | 3 | 100%

## SPRINT2
SPRINT 2 |  |  | Start | 19/5/2015
|  |  | End | 25/5/2015
No. | Task | Description | PIC | Status | Est | Day
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | <Client> Integrating google plus login function | Get user details and their friends | HungLV | Inprocess | 10 |  |  |  |  | 7 | 4
2 | <Client> Integrating facebook login function | Get user details and their friends | HungLV | Inprocess | 10 | 5
3 | Design register UI |  | HungLV | Finished | 4 |  |  | 4 |  |  |  | 0
4 | <Client> Register function |  | HungLV | Inprocess | 8 |  |  | 6
5 | <Client> Get current user position function | Android Location API using Google Play Services | KhuongMH | Finished | 14 | 6 | 4 | 3 | 0
6 | <Client> JSON parser function |  | KhuongMH | Finished | 4 | 0
7 | <Client> Send, receive chat/message function |  | KhuongMH | Inprocess | 14 |  | 13 | 9
8 | <Client> Notification function |  | KhoaVNA | Inprocess | 12 | 10 | 8 | 6
9 | <Client> Profile management function | Allow user update, their profile | KhoaVNA | Not Start | 12
10 | Report 2 |  | KhoaVNA | Finished | 8 | 6 | 5 | 3 | 0
11 | <Server> Webservice for retreive user information | Login, register , and profile info | ThangPV | Inprocess | 20 | 18 |  | 16 | 12 | 10 | 9 | 8
12 | Design Neo4j Database |  | ThangPV | Finished | 8 |  |  |  | 6 | 4 | 2 | 0
13 | Design Admin Dashboard |  | ThangPV | Finished | 4 | 2 | 1 | 0
14 | Design chat UI | Continue from SPRINT 1 | KhuongMH | Finished | 4 | [6 empty] | 0
15 | Design login/social network connection | Continue from SPRINT 1, Transfer from HungLV | ThangPV | Finished | 4 |  | 0
16 | Design setting user profile | Continue from SPRINT 1 | HungLV | Inprocess | 4
SPRINT REPORT
SPRINT TASKS
| Total Task | 16
| Finished | 8
| Inprocess | 8
TEAM PERFORMANCE
| Member | Total Task | Finished | Percent | Point
| ThangPV | 8 | 7 | 87.5% | 90% | 88.75%
| KhuongMH | 4 | 3 | 75% | 90% | 82.5%
| HungLV | 4 | 1 | 25% | 30% | 27.5%
| KhoaVNA | 3 | 1 | 33.33% | 50% | 41.67%

## SPRINT3
SPRINT 3 |  |  | Start | 27/5/2015
|  |  | End | 2015-02-06
No. | Task | Description | PIC | Status | Est | Day
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | <Client> Integrating google plus login function | Continue from SPRINT 2 Transfer from HungLV | KhuongMH | Finished | 12 | 10 | 10 | 0
2 | <Client> Integrating facebook login function | Continue from SPRINT 2 Transfer from HungLV | KhuongMH | Inprocess | 12 | 10 | 8 | 8 | 8 | 8 | 8 | 8
3 | <Client> Register function | Continue from SPRINT 2 Transfer from HungLV | ThangPV | Inprocess | 12 | 10 | 10 | 10 | 10 | 10 | 10 | 10
4 | <Client> Notification function | Continue from SPRINT 2 transfer from KhoaVNA | ThangPV | Inprocess | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
5 | <Client> Profile management function | Continue from SPRINT 2 transfer from KhoaVNA | ThangPV | Finished | 15 | 13 | 10 | 8 | 4 | 0
6 | <Server> Webservice for retreive user information | Continue from SPRINT 2 | ThangPV | Finished | 8 | 8 | 8 | 4 | 4 | 0
7 | Design setting user profile | Continue from SPRINT 2 Transfer from HungLV | ThangPV | Finished | 4 | 4 | 4 | 0
8 | System Architecture |  | ThangPV | Finished | 4 | 4 | 4 | 4 | 4 | 4 | 0
9 | <Client> SQLite storage |  | ThangPV | Finished | 20 | 16 | 14 | 10 | 8 | 4 | 4 | 0
10 | Search nearby location function |  | KhuongMH | Finished | 4 | 2 | 0
SPRINT REPORT
SPRINT TASKS
| Total Task | 10
| Finished | 7
| Inprocess | 3
TEAM PERFORMANCE
| Member | Total Task | Finished | Percent | Point
| ThangPV | 7 | 4 | 57.14% | 150% | 103.6%
| KhuongMH | 3 | 2 | 66.67% | 100% | 83.33%
| HungLV | 0 | 1 | #DIV/0! | 30% | 0%
| KhoaVNA | 0 | 1 | #DIV/0! | 50% | 0%

## SPRINT4
SPRINT 4 |  |  | Start | 2015-02-06
|  |  | End | 2015-08-06
No. | Task | Description | PIC | Status | Est | Day
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | <Client> Send, receive chat/message function | Continue from SPRINT 2 | KhuongMH | Inprocess | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
2 | <Client> Integrating facebook login function | Continue from SPRINT 3 | KhuongMH | Finished | 8 | 0
3 | <Client> Algorithm recommended person | Continue from SPRINT 3 | ThangPV | Finished | 10 | 10 | 5 | 0
4 | <Service> Send, receive chat/message function |  | KhuongMH | Not Start | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
5 | <Client> location by real path |  | KhuongMH | Finished | 10 | 8 | 6 | 0
6 | <Service>Execute friends recommendation |  | ThangPV | Finished | 16 | 16 | 16 | 14 | 10 | 8 | 4 | 0
7 | <Client> Get list friend via facebook | Get list friend who used this app only | KhuongMH | Inprocess | 10 | 6 | 0
8 | <Client> Get list friend via web service |  | ThangPV | Finished | 8 | 8 | 4 | 0
SPRINT REPORT
SPRINT TASKS
| Total Task | 8
| Finished | 5
| Inprocess | 3
TEAM PERFORMANCE
| Member | Total Task | Finished | Percent | Point
| ThangPV | 3 | 3 | 100% | 100% | 100%
| KhuongMH | 5 | 2 | 40% | 100% | 70%
| HungLV | 0 | 0 | #DIV/0! | 30% | 0%
| KhoaVNA | 0 | 0 | #DIV/0! | 50% | 0%

## SPRINT5
SPRINT 4 |  |  | Start | 2015-09-06
|  |  | End | 15/6/2015
No. | Task | Description | PIC | Status | Est | Day
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | <Client> Send, receive chat/message function | Continue from SPRINT 2 | KhuongMH | Inprocess | 18
2 | <Service> Send, receive chat/message function | Continue from SPRINT 4 | KhuongMH | Not Start | 10
3 | Get list friend via facebook | Continue from SPRINT 4 | KhuongMH | Inprocess | 10
4 | Register function |  | KhuongMH | Not Start | 5
6 | Update profile function |  | KhuongMH | Not Start | 5
5 | Show recommended person | Using Redis | ThangPV | Inprocess | 5 | 5 | 5
7 | Search, add new friend function |  | ThangPV | Not Start | 10 | 10 | 10
8 | Setting profile, save setting, datting recommendation options |  | ThangPV | Inprocess | 15 | 10 | 8
SPRINT REPORT
SPRINT TASKS
| Total Task | 8
| Finished | 0
| Inprocess | 0
TEAM PERFORMANCE
| Member | Total Task | Finished | Percent
| ThangPV | 0 | 0 | #DIV/0!
| KhuongMH | 0 | 0 | #DIV/0!
| HungLV | 0 | 0 | #DIV/0!
| KhoaVNA | 0 | 0 | #DIV/0!

## Project Coreflow
4 main coreflow are listed below:
1 | Create user profile (connect automatically with their social network) | KhoaVNA
2 | Manage friends list
3 | Scan near-by locations to find people around the user | ThangPV
4 | Matching user’s interest and profile with others
5 | Suggest user’s people they might want to meet based on their friend’s connections | HungLV
6 | Real time chat & notification when events happen | KhuongMH

## Question
1 | Scan near-by location / Matching user's interest and profile with other là 2 function khác nhau hay là 1 ( trong khi scan thì chỉ suggest những user nào match)
2 | Create user profile. This feature should connect automatically to current user account on other social sites [Facebook, Google+, ..) là cho login qua facebook, google thôi hay là có thêm việc lấy list friends có sử dụng app này??
3 | get location khi ma nguoi do ko su dung app
4 | get current location

## Member
ThangPV
KhuongMH
HungLV
KhoaVNA

## TaskStatus
Not Start
Inprocess
Wait for Approve
Finished