## Product Backlog
MOBILE DATING APPS
Items | Features | Details
1 | Create User Profile | Register new account
Mapping current account and friend list from social network (facebook, google+)
Edit profile info: Interest, gender, location,…
2 | Manage Friends List | Search add new friends
Modify friend list (unfriends, block..)
3 | Scan near-by location by matching user's interest & profile | Show current location map and display friends which nearby user.
View profile other people near by you who match your profile
4 | Suggest new friends base on friends connection | Suggest user you might want to meet base on your current friend connection
5 | Realtime chat | Realtime chat, communicate with available friends
View chat history
6 | Notification | Receive notification when their friends are near by
Chat notification
7 | Recommender System | Build a recommerder system to suggest friends base on user profile similarity

## SPRINT1
SPRINT 1 |  |  | Start | 2015-12-05
|  |  | End | 18/5/2015
No. | Task | Description | PIC | Status | Est. | Day
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Design mockup UI |  | ThangPV | Finished | 4 | 4
2 | Design main layout |  | ThangPV | Finished | 16 |  | 5 | 5 | 5 | 2
3 | Design UseCase |  | ThangPV | Inprocess | 4 | [5 empty] | 4
4 | Design ERD |  | ThangPV | Inprocess | 4 | [5 empty] | 2
5 | Design chat UI | v | KhuongMH | Inprocess | 14 | 5 | 2 | 2
6 | Design scan nearby user UI | v | KhuongMH | Not Start | 14
7 | Design login/social network connection | v | HungLV | Wait for Approve | 14 |  | 2 | 2 | 2 |  | 4 | 2
8 | Design setting user profile | v | HungLV | Inprocess | 14 |  | 2 | 2 | 2 |  | 4 | 2
9 | Design friends list UI | v | KhoaVNA | Inprocess | 14 |  |  | 4 | 6 | 4 |  | 1
10 | Design Utilities layout | v | KhoaVNA | Inprocess | 14 |  |  |  |  | 2 | 4 | 2
11 | Report 1 |  | KhoaVNA | Finished | 4 | 2 | 0.5 | 0.5
12 | Design Web |  | ThangPV | Inprocess |  |  |  |  | 2 | 2 | 2
SPRINT REPORT
SPRINT TASKS
| Total Task | 12
| Finished | 0
| Inprocess | 0
TEAM PERFORMANCE
| Member | Total Task | Finished | Percent
| ThangPV | 0 | 0 | #DIV/0!
| KhuongMH | 0 | 0 | #DIV/0!
| HungLV | 0 | 0 | #DIV/0!
| KhoaVNA | 0 | 0 | #DIV/0!

## SPRINT2
SPRINT 2 |  |  | Start | 19/5/2015
|  |  | End | 26/5/2015
No. | Task | Description | PIC | Status | Est | Day
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
1
2
3
4
5
6
7
8
9
10
SPRINT REPORT
SPRINT TASKS
| Total Task | 10
| Finished | 0
| Inprocess | 0
TEAM PERFORMANCE
| Member | Total Task | Finished | Percent
| ThangPV | 0 | 0 | #DIV/0!
| KhuongMH | 0 | 0 | #DIV/0!
| HungLV | 0 | 0 | #DIV/0!
| KhoaVNA | 0 | 0 | #DIV/0!

## SPRINT3
SPRINT 3 |  |  | Start | 19/5/2015
|  |  | End | 26/5/2015
No. | Task | Description | PIC | Status | Est | Day
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
1
2
3
4
5
6
7
8
9
10
SPRINT REPORT
SPRINT TASKS
| Total Task | 10
| Finished | 0
| Inprocess | 0
TEAM PERFORMANCE
| Member | Total Task | Finished | Percent
| ThangPV | 0 | 0 | #DIV/0!
| KhuongMH | 0 | 0 | #DIV/0!
| HungLV | 0 | 0 | #DIV/0!
| KhoaVNA | 0 | 0 | #DIV/0!

## Project Coreflow
4 main coreflow are listed below:
1 | Create user profile (connect automatically with their social network) | KhoaVNA
2 | Manage friends list
3 | Scan near-by locations to find people around the user | ThangPV
4 | Matching user’s interest and profile with others
5 | Suggest user’s people they might want to meet based on their friend’s connections | HungLV
6 | Real time chat & notification when events happen | KhuongMH

## Question
1 | Scan near-by location / Matching user's interest and profile with other là 2 function khác nhau hay là 1 ( trong khi scan thì chỉ suggest những user nào match)
2 | Create user profile. This feature should connect automatically to current user account on other social sites [Facebook, Google+, ..) là cho login qua facebook, google thôi hay là có thêm việc lấy list friends có sử dụng app này??
ilike

## Member
ThangPV
KhuongMH
HungLV
KhoaVNA

## TaskStatus
Not Start
Inprocess
Wait for Approve
Finished